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GREENFAITH 2026 WORPLAN PROGRESS REPORT

	COUNTRY /ORGANIZER NAME
	REPORTING PERIOD
	SUBMISSION DATE

	TANZANIA
	MAY 2026
	13th May 2026



1. Activity 1

	1. PROGRESS SUMMARY/ ACTIVITY TITLE

	Title: Empowering Indigenous Faith Leadership and Grassroots Organizing for a Just Energy Transition
Summary (of Synopsis): This initiative brought together faith leaders and Indigenous people from Dodoma, Manyara, Tanga, Singida, and Tabora, where communities affected by EACOP from the indigenous communities gathered in Napilikunya village, Kiteto district, from this engagement it was revealed that indigenous people remain excluded from decision-making when it comes to energy projects. Six GreenFaith Circles were established and Training-of-Trainers (TOT) programs for 38 Indigenous and faith leaders was held, especially women and youth, built advocacy, interfaith collaboration, and community mobilization for a just, inclusive, and equitable energy transition in Tanzania.

	2. ACHIEVEMENTS:
Summary of all activities carried out, or of key deliverables and results obtained, during the reporting periods. Include quantitative information 
	[Project Sub-Activity No. 1] Establishment of GreenFaith Circles and Grassroots Mobilization
• Six GreenFaith Circles were established across Dodoma (1 circle), Manyara (2 circles), Tanga (1 circle), Singida (1 circle, and Tabora (1 circle) to strengthen grassroots and Indigenous climate justice organizing.

• Thirty-eight Indigenous and faith leaders, including women and youth representatives, participated in Training-of-Trainers (ToT) sessions on climate justice, EACOP impacts, community advocacy, and just energy transition approaches.

• Community awareness sessions and interfaith dialogues increased local engagement on fossil fuel expansion, environmental protection, and Indigenous rights.

• Grassroots networks were strengthened through coordinated organizing, peer learning, and community exchange initiatives.

• Indigenous knowledge systems and faith-based approaches were integrated into advocacy efforts, improving community participation in public and policy discourse related to energy transition and climate justice.

[Project Sub-Activity No. 2] Press Release and Media Engagement
• Developed and disseminated press releases highlighting the impacts of EACOP and fossil fuel expansion on Indigenous and grassroots communities in Dodoma, Manyara, Tanga, Singida, and Tabora.
• Increased public awareness on climate justice, Indigenous rights, and the need for a just energy transition through media engagement and faith-based advocacy messaging.
• Strengthened visibility of GreenFaith Circles and community-led organizing efforts by engaging local media outlets, civil society actors, and faith leaders.
• Amplified voices of women, youth, and Indigenous leaders advocating for inclusive participation in environmental and energy-related decision-making processes.

	3. LEARNING:
Describe the challenges and lessons recorded during the reporting period.
	During the reporting period, several challenges affected the implementation of project activities. Limited awareness of climate justice and energy transition issues among some community members initially slowed participation and engagement. Geographic distance between target regions increased coordination and travel costs, while language and cultural differences required additional time to ensure inclusive communication with Indigenous communities such as the Akie, Maasai, and Taturu. In some areas, fear of speaking openly about EACOP and fossil fuel impacts also limited early community participation.
Key lessons emerged from these experiences. Faith leaders and respected community representatives play a critical role in building trust and encouraging community engagement on sensitive environmental and social issues. The Training-of-Trainers (ToT) approach proved effective in strengthening local ownership and sustainability, as trained leaders were able to transfer knowledge within their communities. The project also demonstrated that integrating Indigenous knowledge systems, faith values, and grassroots organizing strengthens advocacy efforts and improves community participation in climate justice and energy transition discourse. Prioritizing women and youth increased inclusivity and broadened local leadership in community mobilization activities.

	4. RECOMMENDATIONS:
How can the project be adjusted to enhance its performance and impact?
	To enhance project performance and impact, greater investment should be made in continuous community sensitization and follow-up engagement to deepen understanding of climate justice, EACOP-related impacts, and just energy transition issues. Expanding the number of GreenFaith Circles and strengthening coordination between regions would improve grassroots mobilization and collective advocacy.
Additional resources should be allocated for translation, local facilitation, and culturally responsive communication approaches to ensure effective participation of Indigenous communities, including the Akie, Maasai, and Taturu. Increasing support for women- and youth-led initiatives would further strengthen inclusive leadership and long-term sustainability.
The project would also benefit from stronger partnerships with media organizations, civil society networks, and policy actors to amplify community voices and influence public discourse and decision-making processes. Regular mentorship, refresher trainings, and exchange visits among trained leaders are recommended to sustain momentum, strengthen peer learning, and improve advocacy effectiveness at the community and national levels.

	5. SUPPORTING DOCUMENTS: 
List all supporting documents accompanying your report, such as activity reports, TORs, and Attendance List
Including Google Drive Photo Link
	1. Attendance List
2. Policy Briefs 
3. Activity report 

	6. MEDIA LINK: (TV/Radio/Newspapers)
	1. https://www.facebook.com/share/p/18rd7yyeDA/ 
2. https://www.instagram.com/p/DYPIdh5g1Fn/?igsh=MWw1NDdyNXhxZzdqcg==
3. https://www.ippmedia.com/nipashe/habari/kitaifa/read/ajenda-matumizi-nishati-safi-yazidi-kupenya-vijijini-2026-05-12-132430
4. 

	7. BUDGET (ACTIVITY NUMBER CHARGED ON COUNTRY2026 WORKPLAN)
	$ 3000 (From the Tanzania ETF work plan)






2. Activity II
	1. PROGRESS SUMMARY/ ACTIVITY TITLE

	Title:


Summary (of Synopsis):



	2. ACHIEVEMENTS:
Summary of all activities carried out or key deliverables and results obtained during the reporting periods. Include quantitative information 
	[Project Activity No] [Project Activity Description]
· Summary of output and result 1


	3. LEARNING:
Describe the challenges and lessons recorded during the reporting period.
	

	4. RECOMMENDATIONS:
How can the project be adjusted to enhance its performance and impact?
	

	5. SUPPORTING DOCUMENTS: 
List all supporting documents accompanying your report, such as activity reports, TORs, and Attendance List

Including Google Drive Photo Link
	

	6. MEDIA LINK: (TV/Radio/Newspapers)
	

	7. BUDGET (ACTIVITY NUMBER CHARGED ON COUNTRY2024  WORKPLAN)
	





3. Activity III
	1. PROGRESS SUMMARY/ ACTIVITY TITLE

	Title:


Summary (of Synopsis):



	2. ACHIEVEMENTS:
Summary of all activities carried out or key deliverables and results obtained during the reporting periods. Include quantitative information 
	[Project Activity No] [Project Activity Description]
· Summary of output and result 1


	3. LEARNING:
Describe the challenges and lessons recorded during the reporting period.
	

	4. RECOMMENDATIONS:
How can the project be adjusted to enhance its performance and impact?
	

	5. SUPPORTING DOCUMENTS: 
List all supporting documents accompanying your report, such as activity reports, TORs, and Attendance List

Including Google Drive Photo Link
	

	6. MEDIA LINK: (TV/Radio/Newspapers)
	

	7. BUDGET (ACTIVITY NUMBER CHARGED ON COUNTRY2024  WORKPLAN)
	





4. Activity IV
	1. PROGRESS SUMMARY/ACTIVITY TITLE

	Title:


Summary (of Synopsis):



	2. ACHIEVEMENTS:
Summary of all activities carried out or key deliverables and results obtained during the reporting periods. Include quantitative information 
	[Project Activity No] [Project Activity Description]
· Summary of output and result 1


	3. LEARNING:
Describe the challenges and lessons recorded during the reporting period.
	

	4. RECOMMENDATIONS:
How can the project be adjusted to enhance its performance and impact?
	

	5. SUPPORTING DOCUMENTS: 
List all supporting documents accompanying your report, such as activity reports, TORs, and Attendance List

Including Google Drive Photo Link
	

	6. MEDIA LINK: (TV/Radio/Newspapers)
	

	7. BUDGET (ACTIVITY NUMBER CHARGED ON COUNTRY2024  WORKPLAN)
	





5. Activity V

	1. PROGRESS SUMMARY/ ACTIVITY TITLE

	Title:


Summary (of Synopsis):



	2. ACHIEVEMENTS:
Summary of all activities carried out or key deliverables and results obtained during the reporting periods. Include quantitative information 
	[Project Activity No] [Project Activity Description]
· Summary of output and result 1


	3. LEARNING:
Describe the challenges and lessons recorded during the reporting period.
	

	4. RECOMMENDATIONS:
How can the project be adjusted to enhance its performance and impact?
	

	5. SUPPORTING DOCUMENTS: 
List all supporting documents accompanying your report, such as activity reports, TORs, and Attendance List

Including Google Drive Photo Link
	

	6. MEDIA LINK: (TV/Radio/Newspapers)
	

	7. BUDGET (ACTIVITY NUMBER CHARGED ON COUNTRY2024  WORKPLAN)
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  1.   Activity 1    

1.   PROGRESS  SUMMARY /  ACTIVITY TITLE    Title :   Empowering Indigenous Faith Leadership and Grassroots Organizing for a Just Energy  Transition   Summary (of Synopsis) :   Thi s initiative brought together faith leaders   and Indigenous  people from   Dodoma, Manyara, Tanga, Singida, and Tabora, where communities  affected by EACOP  from the indigenous communities gathered in Napilikunya village,  Kiteto district , from this eng agement it was revealed that indigenous  people  remain   excluded from decision - making   when it comes to energy projects . Six GreenFaith  Circles   were  established  and   Training - of - Trainers   (TOT)   programs for 38 Indigenous and  faith leaders   was he ld , e specially women and youth, built   advocacy, interfaith  collaboration, and community mobilization for a just, inclusive, and equitable energy  transition in Tanzania.  

2.   ACHIEVEMENTS :   Summary of all activities carried  out , or of key deliverables and  results obtained,   during the  reporting periods . Include  quantitative information   [Project  Sub - Activity No. 1] Establishment of GreenFaith Circles and Grassroots  Mobilization   • Six GreenFaith Circles were established across Dodoma   ( 1   circle ) , Manyara   (2 circles) ,  Tanga   (1 circle) , Singid a  (1 circle , and Tabora   (1 circle)   to strengthen grassroots and  Indigenous climate justice organizing.     • Thirty - eight Indigenous and faith leaders, including women and youth representatives,  participated in Training - of - Trainers (ToT) sessions on climate justice, EACOP impacts,  community advocacy, and just energy transition approaches.     • Community awareness sessions and interfaith dialogues increased local engagement  on fossil fuel expansion, environmental protection, and Indigeno us right s .     • Grassroots networks were strengthened through coordinated organizing, peer  learning, and community exchange initiatives.     • Indigenous knowledge systems and faith - based approaches were integrated into  advocacy efforts, improving community participation in public and policy discourse  related to energy transition and climate justice.     [Project Sub - Activity No.  2] Press Release and Media Engagement   • Developed and disseminated press releases highlighting the impacts of EACOP and  fossil fuel expansion on Indigenous and grassroots communities in Dodoma, Manyara,  Tanga, Singida, and Tabora.   • Increased public awareness on climate justice, Indigenous rights, and the need for a  just energy transition through media engagement and faith - based advocacy 

